## Task Tracker
CRISIS PRESENTATION CRM — Vendor Backed Out: 2 Weeks to Event
Presentation Topic: Crisis Handling ¦ Emergency Vendor Replacement Strategy
# | Task / Slide Section | Owner | Role | Status | Priority | Due Date | Notes / Details | Technicals / Risk
1 | Opening Slide & Agenda | Reanee | Project Lead / Coordinator | Done | High | 2025-06-18 | Intro slide, agenda overview, tone setting for crisis narrative | Ensure slide loads on both Windows and Mac. Have PDF backup ready.
2 | Crisis Background & Problem Statement | Marco | Researcher | Done | High | 2025-06-18 | Define the crisis: vendor backed out 14 days before event. Set urgency. | Source credible stats on vendor failure rates. Cite sources on slide.
3 | Stakeholder Impact Analysis | Lena | Content Writer | Done | High | 2025-06-18 | Who is affected? attendees, sponsors, organizers. Visual impact map. | Check if org chart graphic renders correctly. Embed, do not link.
4 | Immediate Response Framework (First 48hrs) | Marco | Researcher | Done | High | 2025-06-18 | Step-by-step actions: notify team, assess contracts, begin vendor search. | Slide animations must not auto-run. Set to click-to-advance only.
5 | Replacement Vendor Strategy & Sourcing | Trisha | Content Writer | Done | High | 2025-06-18 | How to find, vet, and onboard a replacement vendor in under 2 weeks. | Include comparison table. Test table formatting on projector resolution.
6 | Budget Reallocation & Cost Management | James | Finance / Data | Done | High | 2025-06-18 | Contingency budget slide. Show cost impact and reallocation options. | All figures must be confirmed. Avoid placeholder numbers on final deck.
7 | Communication Plan (Internal & External) | Lena | Content Writer | Done | Medium | 2025-06-18 | Scripts and timelines for notifying vendors, sponsors, and attendees. | Check for typos in sample email templates. Proofread twice.
8 | Risk Register & What Could Go Wrong | Reanee | Project Lead / Coordinator | Done | Medium | 2025-06-18 | Identify 5 risks: no vendor found, budget overrun, attendee dropout, PR damage, timeline slip. | This is the technical risk slide. Must be airtight.
9 | Resolution Timeline & Milestones | James | Finance / Data | Done | Medium | 2025-06-18 | Visual Gantt-style timeline from crisis day to event day. | Gantt chart must be embedded as image, not linked Excel file.
10 | Lessons Learned & Prevention Framework | Trisha | Content Writer | Done | Low | 2025-06-18 | Post-crisis review: what to do differently. Vendor contract checklist. | Keep concise. 1 slide max. Avoid being preachy.
11 | Closing & Q&A Slide | Reanee | Project Lead / Coordinator | Done | Low | 2025-06-18 | Thank you slide, presenter contacts, open floor for questions. | Have a blank slide ready after Q&A in case of extended discussion.
12 | Full Deck Review & Rehearsal | All | Full Team | Done | High | 2025-06-18 | Full run-through. Check transitions, timing, flow, and consistency. | Rehearse in the actual room or platform. Test clicker/presenter mode.
13 | Backup Deck & Technical Prep | Reanee | Project Lead / Coordinator | Done | High | 2025-06-18 | Save deck as PDF. Upload to Drive. Test on venue laptop. | Bring USB with deck. Test HDMI and adapter. Have charger ready.
14 | Final Presentation Delivery | All | Full Team | Done | High | 2025-06-19 | Present to stakeholders. Reanee to manage timing and transitions. | Reanee monitors time. Marco advances slides. Others on standby for Q&A.

## Team Overview
TEAM OVERVIEW - Presentation Crisis CRM
Name | Role | Strengths | Slides Assigned | Tasks Done | Notes
Reanee | Project Lead / Coordinator | Organization, systems, risk management | Opening, Risk Register, Closing, Backup & Tech Prep, Delivery | 5 / 5 | Manages CRM, tracks all progress, owns technicals checklist
Marco | Researcher | Data gathering, problem framing, detail-oriented | Crisis Background, Immediate Response Framework, Delivery | 3 / 3 | Strong on research; needs to keep slides concise
Lena | Content Writer | Storytelling, communication, empathy framing | Stakeholder Impact, Communication Plan, Delivery | 3 / 3 | Ensure tone is professional not emotional
Trisha | Content Writer | Copywriting, structure, visual flow | Vendor Strategy, Lessons Learned, Delivery | 3 / 3 | Coordinate with Marco on vendor slide overlap
James | Finance / Data | Numbers, budget analysis, data visualization | Budget Reallocation, Timeline / Milestones, Delivery | 3 / 3 | Confirm all figures with team before June 18

## Risk & Technicals
RISK REGISTER & TECHNICAL CHECKLIST
Risk | Likelihood | Impact | Mitigation | Owner
No replacement vendor found in time | Medium | High | Pre-identify 3 backup vendors on Day 1. Assign Trisha to shortlist by Day 2. | Trisha
Budget overrun from emergency sourcing | High | High | James to set hard budget ceiling. Escalate to lead if exceeded. | James
Attendee or sponsor dropout due to uncertainty | Medium | Medium | Lena to draft holding comms by Day 1. Keep messaging calm and confident. | Lena
Presentation deck technical failure on the day | Low | High | PDF backup on USB and Google Drive. Test on venue equipment Day 2 | Reanee
Team misalignment on slide content or tone | Medium | Medium | Full deck review on Day 2. Reanee to flag inconsistencies by Day 1. | Reanee
Key team member unavailable close to deadline | Low | High | All slides saved on shared Drive. Anyone can pick up with notes. | All
LEGEND: | High Impact | Medium Impact | Low Impact